## Sheet1
Financial Analysis for HeartCare
Created by: Marco Calenda, Raimondo Rapacciuolo |  | Date: 29/10/2022
Note: Change the inputs, shown in green below (i.e. interest rate, number of years, costs, and benefits). Be sure to double-check the formulas based on the inputs.
Discount rate | 8%
Assume the project is completed in Year 0 |  |  | Year
| 0 | 1 | 2 | 3 | Total
Costs | 18750 | 5000 | 5000 | 5000
Discount factor | 1 | 0.93 | 0.86 | 0.79
Discounted costs | 18750 | 4650 | 4300 | 3950 | 31650
Benefits | 0 | 18450 | 18450 | 18450
Discount factor | 1 | 0.93 | 0.86 | 0.79
Discounted benefits | 0 | 17158.5 | 15867 | 14575.5 | 47601
Discounted benefits - costs | -18750 | 12508.5 | 11567 | 10625.5 | 15951 | NPV
Cumulative benefits - costs | -18750 | -6241.5 | 5325.5 | 15951 |  | Net Present Value
ROI | 50.4%
Payback in Year 2
Assumptions
Assumiamo che il progetto venga realizzato in 3 mesi
Reources | Cost/Hour | Hour | Number | Partial
Team Member | 50 | 50 | 6 | 15000
Total project cost |  |  |  | 15000
Benefits | Cost/Hour | Hour saved/day | Number | Partial
Personale medico | 12.5 | 0.3 | 20 | 75
Total annual projected benefits |  |  |  | 18450
Total annual maintenance costs |  |  |  | 5000